## Ke hoach 4 tuan
KE HOACH PHAN CONG 4 TUAN - DU AN CASESTUDY ENGINE
Nguon tham chieu | partition.md, FUNCTIONAL_MAP.md, STATE_SPEC.md, README.md, CASESTUDY_ENGINE_GUIDE.md
Pham vi | Chia cong viec 4 tuan cho 5 member theo partition da cung cap
Tuan | Member | Vai tro | Cong viec chinh | Output cuoi tuan | Phu thuoc / Phoi hop | Ghi chu
Tuan 1 | Thinh | Backend AI & nen tang | Tao khung FastAPI; ket noi MongoDB Atlas; lam API register/login; tao model user/case co ban; khoi tao skeleton LangGraph 4 agent | Auth chay end-to-end; backend co skeleton agent va DB | Phoi hop Vinh de chot API contract; Nhung de test auth | Theo partition backend + AI
Tuan 1 | Vinh | Unity Core, Networking | Dung SimulationManager, EventManager; setup flow state MainMenu -> Login -> Library; tao model C# map JSON theo STATE_SPEC; khoi tao networking layer | Unity login duoc vao backend; co core state va networking skeleton | Phoi hop Thinh ve endpoint/auth; FE A ve UI Auth | Lead giu Scripts/Core
Tuan 1 | FE Dev A | UI/UX Auth & Library | Lam UI Login/Register bang UI Toolkit; tao khung Asset Library; thong nhat style guide UI chung | Skeleton UI cho Auth va Library | Phoi hop Vinh de bind state; khong sua Core | Moi man hinh tach .uxml/.uss/controller
Tuan 1 | FE Dev B | Designer, Simulator, Scene 3D | Setup scene 3D hotel lobby co ban; chuan bi prefab moi truong/nhan vat; khoi tao khung UI Designer va Simulator; prototype raycast chon object | Co scene 3D co ban va prototype Designer/Simulator | Phoi hop Vinh ve object interaction | Tap trung scene + tooling
Tuan 1 | Nhung | Prompt, Data Config, QA | Viet 1-2 file case JSON mau dung schema; soan persona traits, policies, reward rules; viet prompt nhap cho 4 agent; test auth API bang Swagger/Postman | Co case JSON mau hop le va prompt nhap | Phoi hop Thinh de test endpoint | Can bam sat STATE_SPEC
Tuan 2 | Thinh | Backend AI & nen tang | Hoan thien CRUD case; cai luong LangGraph tra loi 1 luot hoi thoai; gan reward_system.rules vao Judge Agent; xay khung RAG doc policies | Tao/luu case duoc; backend tra loi hoi thoai 1 vong | Phoi hop Nhung ve reward/policy; Vinh ve parse state | Tap trung do on dinh API
Tuan 2 | Vinh | Unity Core, Networking | Hoan thien parse/serialize JSON state giua Unity va backend; toi uu networking, timeout, token; gan event bus cho Library/Designer/Simulator; setup collider + smart object interaction | JSON contract chay on dinh, interaction co ban hoat dong | Phoi hop Thinh va FE B | Bam theo STATE_SPEC
Tuan 2 | FE Dev A | UI/UX Auth & Library | Hoan thien Asset Library: list Env/Persona, card view, click xem chi tiet; bo sung loading/error/empty state | Asset Library xem duoc du lieu | Phoi hop Vinh ve data binding | Theo task Asset Library trong guide
Tuan 2 | FE Dev B | Designer, Simulator, Scene 3D | Lam man hinh Designer: chon env, chon persona, panel chinh traits; keo-tha object trong scene; nut Save Case goi backend | Designer tao/lưu case duoc | Phoi hop Vinh va Thinh de save case | Task kho nhat, can uu tien
Tuan 2 | Nhung | Prompt, Data Config, QA | Hoan thien 3-5 case mau; viet policy nghiep vu khach san; tinh chinh prompt de persona khong thoat vai; test JSON validity va trigger thuong/phat | Bo case test chuan schema va reward | Phoi hop Thinh de dua data vao backend | Tap trung data chat luong
Tuan 3 | Thinh | Backend AI & nen tang | Hoan thien multi-agent loop nhieu luot chat; gan active_memory, history, interacted_objects; tich hop RAG grounding/citation; toi uu Judge & Reward | Flow hoi thoai nhieu luot on dinh | Phoi hop Nhung de test hallucination | Tap trung state runtime
Tuan 3 | Vinh | Unity Core, Networking | Ket noi runtime_state that tu Unity len backend sau moi tuong tac; dieu phoi luong Simulator on dinh; tich hop animation trigger/state event; hoan thien NavMesh va object interaction nen | Simulator sync state on dinh, khong crash khi chat lien tuc | Phoi hop FE B va Thinh | Tap trung hieu nang client
Tuan 3 | FE Dev A | UI/UX Simulator | Hoan thien UI Simulator phan chatbox, log hoi thoai, score realtime; tao feedback panel/tong ket cuoi buoi; toi uu layout UI Toolkit | UI Simulator va Summary hoan chinh | Phoi hop Vinh de nhan event va data | Chiu trach nhiem phan UI 2D
Tuan 3 | FE Dev B | Designer, Simulator, Scene 3D | Lam tuong tac 3D/UI: hover, click, tooltip, world-space bubble; gan UI voi smart_objects; hoan thien Designer UX va prefab co script | Tuong tac 3D-UI hoat dong trong scene | Phoi hop Vinh ve raycast/event | Tap trung trai nghiem truc quan
Tuan 3 | Nhung | Prompt, Data Config, QA | Kiem thu hoi thoai dai; test hallucination, test giu ngu canh; viet them case edge-case; soat reward/penalty; ghi bug va de xuat sua prompt/data | Danh sach bug va bo test edge-case | Phoi hop Thinh de fix prompt/agent | Tap trung chat luong AI
Tuan 4 | Thinh | Backend AI & nen tang | Toi uu hieu nang API, logging, error handling; on dinh LangGraph workflow; toi uu RAG va format response cho Unity de parse; chuan bi tai lieu backend/demo API | Backend demo-ready va tai lieu API | Phoi hop ca nhom de fix integration | Chot ban backend
Tuan 4 | Vinh | Unity Core, Networking | Toi uu memory, giam lag khi sync state; fix bug flow state va networking; chot core branch de merge; kiem thu tich hop toan bo | Client on dinh, integration pass | Phoi hop Lead merge code | Phan chot tong the frontend core
Tuan 4 | FE Dev A | UI/UX Auth, Library, Summary | Polish UI: spacing, font, mau, hieu ung co ban; hoan thien Home/Auth/Library/Summary UI; fix bug hien thi va validate input | UI polished de demo | Phoi hop Vinh va FE B | Tap trung polish giao dien
Tuan 4 | FE Dev B | Designer, Simulator, Scene 3D | Polish Designer/Simulator UI + scene; toi uu raycast, tooltip, panel tuong tac; chot prefab va scene demo | Scene demo va tuong tac 3D hoan chinh | Phoi hop Vinh va FE A | Chot ban demo 3D
Tuan 4 | Nhung | Prompt, Data Config, QA | Regression test toan he thong; chot bo JSON case chinh thuc; viet checklist demo, expected result va tai lieu test nhanh | Bo case chinh thuc va checklist demo | Phoi hop ca nhom truoc demo final | Nguoi giu chat luong cuoi

## Tong quan
TONG QUAN PHAN CONG NHAN SU
Member | Vai tro | So tuan tham gia | Trong tam cong viec | Deliverable chinh
Thinh | Backend AI & nen tang | 4 | FastAPI, MongoDB, JWT, LangGraph, RAG | API auth; CRUD case; multi-agent workflow; RAG; toi uu backend
Vinh | Unity Core, Networking | 4 | SimulationManager, EventManager, JSON contract, networking, physics nen | Core state; networking; runtime sync; performance/integration
FE Dev A | UI/UX Auth, Library, Simulator UI | 4 | UI Toolkit, layout, card view, chatbox, summary UI | Auth UI; Library UI; Simulator UI; polish giao dien
FE Dev B | Designer, Simulator, Scene 3D | 4 | Designer tooling, raycast, world-space UI, prefab/scene | Designer; scene 3D; object interaction; demo scene
Nhung | Prompt, Data Config, QA | 4 | Prompt engineering, JSON case, policy, reward, QA | Bo case JSON; policy; prompt; test plan; regression

## Moc review
CAC MOC REVIEW NOI BO
Thoi diem | Noi dung review | Ket qua mong doi
Cuoi tuan 1 | Review contract du lieu va skeleton he thong | Thong nhat STATE_SPEC, auth chay end-to-end
Giua tuan 2 | Review save/load case va Asset Library | Designer + CRUD case hoat dong co ban
Cuoi tuan 3 | Review flow mo phong hoan chinh | Login -> Library -> Simulation -> Score -> Feedback
Cuoi tuan 4 | Review demo final va merge main | Ban demo on dinh, co tai lieu test/checklist